QUARTERLY UPDATE

| Contract reference no.: | ASI/B7-301/98/679-040 (Asia-Link Programme) |
| --- | --- |
| Project Title: | Strengthening of Institute for Agro-forestry and Watershed Management, Philippines |
| Name of Beneficiary: | University of Wales Bangor (Centre for Arid Zone Studies), UK |
| Period covered by this Quarterly Update: | 3rd May to 3rd August 2004 |
| Due date of this Quarterly Update: | 3rd August 2004 |

I. Introduction

Because of various delays in collating the information from the partners and the fact that the accounts for the project year could  not be prepared until after the end of the project year (3 May – 3 May), the first year accounts, Interim Report, Second Action Plan, Table of Forecast Expenditures and the corresponding Payment Request were not sent to the EU until the end of June. The transfer of the project management to the Philippines, whilst a welcome development, caused further delays in finalising the payment for year 2. This was exacerbated by confusion at CAZS about the arrangements for providing evidence for the audit of the project accounts.

In June (6th to 23rd), the project manager visited DMMMSU in the Philippines. The main purpose of this was to participate in a workshop aimed at collating the results of the various surveys undertaken as part of the background work of the curriculum development activities and course preparation,

II. Description of Activities

Survey of past students and prospective employers (Activity 2)

This activity was completed in month two (June) as planned and a report is available on the internet at http://www.bangor.ac.uk/saiwam/Reports/Reports.htm

The new project editor has been out of the country and the project staff are awaiting his revisions to the reports.

Review of technologies (Activity 3)

The database containing of abstracts of unpublished material at DMMMSU been has completed. Around 300 documents have been entered.  The bibliography can be searched at http://www.bangor.ac.uk/saiwam/Reports/Survey-Reports/Bibliography/Abstracts.htm.

The bibliography has a hyperlinked contents section and is in the process of being indexed.

The new project editor has been out of the country and the project staff are awaiting his revisions.

Documentation of project experience (Activity 4)

This survey was completed around May and the draft report was produced in June. The summary of the findings can be downloaded at http://www.bangor.ac.uk/saiwam/Reports/Reports.htm

The new project editor has been out of the country and the project staff are awaiting his revisions.

Participatory problem analysis (Activity 5)

Writing up of the review of farmer perceptions of their land and water related problems was completed in June as stated in the Intermediate Report. A PowerPoint presentation was given of the results and the summary document is completed but is still undergoing editing before being put onto the internet. However the reports on each of the 20 communities visited is available at

http://www.bangor.ac.uk/saiwam/Reports/Survey-Reports/Farmers/Farmer-surveys.htm

Formulation of courses, module content and learning objectives (Activity 6)

After the presentations of the various surveys were made at the workshop in June, Dr Nelly Antolin, the project coordinator gave a PowerPoint presentation summarising how the various surveys impacted on the curriculum development process. The discussion document is still undergoing revisions. The PowerPoint presentations given at the workshop are available at

http://www.bangor.ac.uk/saiwam/Reports/Reports.htm

DMMMSU staff to go on courses in the EU (Activity 7)

Gabriel Lucero, the former director of the Institute of Agroforestry and Watershed Management who started his M.Comm course in Cork in September has completed his studies and is to submit his dissertation during September.

Development of teaching materials (Activity 8)

This activity has not yet started – partly because of the delay in receiving the funds for Year 2.

Students at EU universities go to DMMMSU (Activity 9)

Another two students – from University of Wales Bangor – went to DMMMSU to undertake their field work for their MScs. One topic concerned land and water constraints to vegetable production and the other was concerned with analysing the literature on deforestation and reforestation. The text of the latter dissertation Is available at http://www.bangor.ac.uk/saiwam/Reports/Reports.htm

III. Other Issues

As always, cash flow continues to be a problem, especially for DMMMSU.